## Timeline chart
Months / Task: Person | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | Farm Management System
A: Azizul
B: Azizul | [32 empty] | Effort = PM = 2.4*(6000/1000)^1.05 = 16
C: Jawadul | [32 empty] | Development time = DM = 2.5*16^0.38 = 8
D: Nasiruddin | [32 empty] | Required number of People = ST = 16/8 = 2
E: Azizul
F: Jahid
G: Jahid
A. Analysis
B. Hardware design
C. Logical & Interface design
D. Coding
E. Testing
F. Installation
G. Maintenance

## Work Tasks
Work Tasks | Month 1 | [19 empty] | Sprint 1 | [19 empty] | Sprint 2 | [19 empty] | Sprint 3 | [19 empty] | Sprint 4 | [19 empty] | Sprint 5 | [19 empty] | Sprint 6 | [19 empty] | Sprint 7
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32
1.1.1.1. Analysis | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T
1.1.1.1.1.1.1. Requirement specification | bar: Week 1 S to Week 2 T
1.1.1.1.1.1.2. Business analysis | bar: Week 3 S to Week 3 T
1.1.1.1.1.1.3. Feasibility study | bar: Week 4 S to Week 4 T
1.1.1.2. Design
1.1.1.2.1.1.1. Hardware design
1.1.1.2.1.1.1.1. Sensor design | bar: Week 5 S to Week 8 T
1.1.1.2.1.1.2. Logical design
1.1.1.2.1.1.2.1. Use case diagram | bar: Week 5 S to Week 5 T
1.1.1.2.1.1.2.2. Class diagram | bar: Week 5 W to Week 6 M
1.1.1.2.1.1.2.3. Activity diagram | bar: Week 6 T to Week 7 S
1.1.1.2.1.1.2.4. Sequence diagram | bar: Week 7 M to Week 7 T
1.1.1.2.1.1.3. User interface design
1.1.1.2.1.1.3.1. Form Designing
1.1.1.2.1.1.3.1.1. Login form | bar: Week 8 S to Week 8 T
1.1.1.2.1.1.3.1.2. Signup form | bar: Week 8 W to Week 8 T
1.1.1.2.1.1.3.1.3. Main menu form | bar: Week 9 S to Week 9 T
1.1.1.2.1.1.3.1.4. Profile form | bar: Week 10 S to Week 10 T
1.1.1.2.1.1.3.1.5. Edit profile form | bar: Week 11 S to Week 11 T
1.1.1.2.1.1.3.1.6. Change Password form | bar: Week 12 S to Week 12 T
1.1.1.2.1.1.3.1.7. Subscription form | bar: Week 13 S to Week 13 T
1.1.1.2.1.1.3.1.8. Transaction backlog form | bar: Week 14 S to Week 14 T
1.1.1.2.1.1.3.1.9. Add Sensor form | bar: Week 15 S to Week 16 T
1.1.1.2.1.1.3.1.10. Sync Data form | bar: Week 17 S to Week 18 T
1.1.1.2.1.1.3.1.11. Add Space form | bar: Week 19 S to Week 20 T
1.1.1.2.1.1.3.1.12. Daily Notifications form | bar: Week 21 S to Week 22 T
1.1.1.2.1.1.3.1.13. Browse General info form | bar: Week 23 S to Week 26 T
1.1.1.2.1.1.3.1.14. Current Recommendations form | bar: Week 27 S to Week 28 T
1.1.1.2.1.1.3.1.15. Analyze form | bar: Week 29 S to Week 30 T
1.1.1.2.1.1.3.1.16. Details form | bar: Week 31 S to Week 32 T
1.1.1.3. Coding
1.1.1.3.1.1.1. Management logic | bar: Week 5 S to Week 5 T; Week 9 S to Week 9 T; Week 13 S to Week 13 T; Week 17 S to Week 17 T; Week 21 S to Week 21 T; Week 25 S to Week 25 T; Week 29 S to Week 29 W
1.1.1.3.1.1.2. Sensor data gathering logic | bar: Week 6 S to Week 6 T; Week 10 S to Week 10 T; Week 14 S to Week 14 T; Week 18 S to Week 18 T; Week 22 S to Week 22 T; Week 26 S to Week 26 T; Week 29 T to Week 30 T
1.1.1.3.1.1.3. Sensor data syncing logic | bar: Week 7 S to Week 7 T; Week 11 S to Week 11 T; Week 15 S to Week 15 T; Week 19 S to Week 19 T; Week 23 S to Week 23 T; Week 27 S to Week 27 T; Week 30 W to Week 31 M
1.1.1.3.1.1.4. Environmental data analyzing logic | bar: Week 8 S to Week 8 T; Week 12 S to Week 12 T; Week 16 S to Week 16 T; Week 20 S to Week 20 T; Week 24 S to Week 24 T; Week 28 S to Week 28 T; Week 31 T to Week 32 S
1.1.1.4. Testing
1.1.1.4.1.1.1. Blackbox testing
1.1.1.4.1.1.2. Functional testing | bar: Week 9 M to Week 10 T; Week 11 M to Week 12 W; Week 13 M to Week 14 T; Week 15 M to Week 16 W; Week 17 M to Week 18 T; Week 19 M to Week 20 T; Week 21 M to Week 22 T; Week 23 M to Week 24 T; Week 25 M to Week 26 T; Week 27 M to Week 28 T; Week 29 M to Week 30 T; Week 31 M to Week 32 T
1.1.1.5. Installation
1.1.1.5.1.1.1. Hardware verification | bar: Week 7 S to Week 8 T; Week 12 S to Week 12 M; Week 16 S to Week 16 M; Week 20 S to Week 20 M; Week 24 S to Week 24 M; Week 28 S to Week 28 M; Week 31 T to Week 32 S
1.1.1.5.1.1.2. Operating System verification | bar: Week 5 S to Week 6 T; Week 12 T to Week 12 T; Week 16 T to Week 16 T; Week 20 T to Week 20 T; Week 24 T to Week 24 T; Week 28 T to Week 28 T; Week 32 M to Week 32 W
1.1.1.6. Maintenance
1.1.1.6.1.1.1. Software maintenance | bar: Week 9 S to Week 10 S; Week 13 S to Week 14 S; Week 17 S to Week 18 S; Week 21 S to Week 22 S; Week 25 S to Week 26 S; Week 29 S to Week 30 S
1.1.1.6.1.1.2. Hardware maintenance | bar: Week 10 M to Week 11 S; Week 14 M to Week 15 S; Week 18 M to Week 19 S; Week 22 M to Week 23 S; Week 26 M to Week 27 S; Week 30 M to Week 31 S
1.1.1.6.1.1.3. Updation | bar: Week 11 M to Week 11 T; Week 15 M to Week 15 T; Week 19 M to Week 19 T; Week 23 M to Week 23 T; Week 27 M to Week 27 T; Week 31 M to Week 31 W; Week 32 T